Neighbourhood Plan Sub-Committee

Monday 8th June 2020 at 6:30pm

AGENDA

- Opening including Public Forum

- Mins of last meeting

- Apologies

- Overview of the Plan

  - Review of actions from previous meeting

- Ian Poole (NP consultant)

  - Given advice on next stages see Other Surveys

- Grant/Finance

  - £8,873

  - HD and KW to confirm funds in the account

  - Tuddenham Press £415 + VAT for 1000 copies in colour of the survey

- AECOM – Locality

  - RlJ and HD had a meeting with Paul Avery from AECOM regarding the Housing Needs Assessment. It is based around data already in existence, Census 2011, local data from BDC. The aim of the document is to establish through data the housing need for Sproughton. Its final use is to form the data structure of the policies we want to produce.

  - AECOM do the entire document and it will take 10-12 weeks.

  - We have two weeks to review the document and make comments

  - May nee to plan an interim meeting to cover the above.

    - Comprises two chapters

      - Type and size of buildings e.g. bedroom numbers, disability, bungalows etc

      - Cost and tenancy e.g. affordable, social, private rent etc

- Survey

  - Many thanks to KS for the recommendation of Tuddenham Press.

  - Survey Excel data consolidation document complete after updates RLJ

- Consultation events:

  - Considered soon to be possible with social distancing

  - Option for virtual consultation

  - YouTube video (HD)

- Media

  - Leaflet drop – Thank you in Intouch mag/websites and social media

  - Poster for notice boards

  - Many thanks to Iain Selby for producing the sign for the Tithe Barn

  - Consideration for “countdown” A-Frame outside Tithe Barn encouraging completion.

- Consideration to be give to other surveys – ACOM

  - Green Spaces – need to start identifying green spaces across the parish, accessible open space, so that an assessment can be made of them. Ian Poole to look at maps and see if I can make some suggestions

    - RLJ has started the Greenspaces document

  - SEA/HRA – no need to worry about this yet – we need to have a draft Plan that can be assessed first.

  - Landscape Assessment – might be worth kicking this off if you have budget/grant? Alison Farmer has done some work for Babergh / Mid Suffolk and she might be able to do more detailed work without incurring her full (quite expensive) costs? RLJ Contacted AF

- To Agree Date & Time of Next Meeting and on-going Frequency of Meetings

- Items for Next Meeting

- Close of Meeting

R Jermyn

Rhona Jermyn, Chair, Sproughton Neighbourhood Plan Sub-Committee