Neighbourhood Plan Minutes from 08th June 2020

Apologies: Simon Curl

Last meetings minutes reviewed and approved - RJ / KS / HD

Update on progress of plan provided by HD:

- Engagement actions have been started.

- Draft vision completed

- Printing of flyers has commenced and all parties will deliver a section to the Parish.

- Flyers to be delivered this weekend.

- Status updates need to go onto the various websites / Intouch magazine / local paper

- RJ to add flyer to community notice board at shop.

- KS to add flyer Millennium Green and Morrisons noticeboard

- AM to add flyer to Nursery noticeboard.

Consultation events:

- Considered soon to be possible with social distancing

- Option for virtual consultation

- YouTube video (HD)

- Survey

  - First draft completed and with Alan Newman for review

  - Already approved by Ian Poole

  - RJ to send to Paul Bryant for review

  - Will be circulated in paper format as quicker than survey monkey

  - RD to request Ian Selby produce sign for Tithe Barn

  - Consideration for “countdown” A-Frame outside Tithe Barn encouraging completion.

  - Survey to be finalised and distributed ASAP

  - Additional interim NP meeting agreed for the 22/06/20 for discussion of any issues around survey and organise distribution of document.

  - Consideration for additional question around protection of greenbelt area – RJ and KS to determine appropriate wording.

  - Trial run to be completed for survey – Mel / Bryan to provide feedback

  - Consideration to be give to other surveys – ACOM

Grant:

- £8,873 has been allocated to the group

- KW – SPC secretary to manage funds

Other Matters:

- Ian Poole has been appointed as “Critical Friend Support”

- No current update on the JLP

- RJ – received no response to her enquiry with CAS but now considered no longer necessary given progress made.

Next meeting set for 18.30 - Monday 6th of July