Sproughton Neighbourhood Plan Meeting Minutes: 12/10/2020

Meeting commenced at 18.36

Apologies – Simon Curl

Declaration of interest for any item on the agenda – none raised

Declaration of any pecuniary interest – none raised

Previous meetings minutes  not yet complete .

Overview of plan provided by Helen:

- Behind schedule for community update – not yet completed, to include update on Pigeon / Taylor Wimpey and JLP. (action Rhona to produce leaflet)

- Update required for In-Touch magazine (action Sharon)

- School survey has been completed – given to children as homework – Maddy and Cara to do inputting.

- Approval from all persons present that the school be given a £100 book voucher as thanks for printing the surveys.

- Consideration for “Next Steps” exhibition in January 2021 – COVID dependant.

- Final version of Housing needs assessment completed.

- Landscape Character Assessment initiated.

- Rhona 2/3 though Green Space Assessment .

- Designs Codes Assessment – still to be completed.

- Green Spaces Assessment – In to decide if they meet the criteria – may need additional evidence to keep all sites in the plan. Football pitch and bowls green to be listed as sports facilities?

- Comment from Ian Poole – he must see any early draft of the plan for review.

- Call for Sites Assessment and Design Codes Assessment – both underway (no costs – being completed by Ben and Una) Ian to see Una’s call for sites draft when completed.

Identification of Non Listed Important Buildings:

- Alms Houses

- The Lock Up

- Old School House

- Reading Room

- Cottage behind the Reading Room

- Harry the Meat’s House ??

- Simon Curl’s house

- Mandolin Manor – Hadleigh Road

- Entrance to Anney Oaks

- Dickie Everett’s House ??

- Cottages on the High Street

- The Shed

- Houses at 7 the High Street

Transport and traffic – can we ask Clive Harris and Andrew Bannon to produce a traffic survey?

Grant update: 70% payment made to Alison Farmer. (Rough draft of document expected by Christmas)

Next meeting : 09/11/20 at 18.30

Items for next meeting:

Overview

Public Consultation

Media

Assessment Update

Concluded 19.40