Sproughton Neighbourhood Plan Meeting Minutes: 15/02/21

Meeting commenced at 18.35

Present – Rhona, Helen, Ken, Sharon and Anne

Apologies – Simon Curl

Declaration of interest for any item on the agenda – none raised

Declaration of any pecuniary interest – none raised

Minutes proposed by Ken and seconded by Helen.

Meeting recorded.

Plan Update from Helen:

- More money to be applied for from the 01/04/20

- Public Engagement – Flyer to be put online site.

- Plan to be published for parishioners prior to sending to BDC for review.

- Pan to updated with parishioner’s comments before sending to BDC.

- Consideration of two public exhibitions to attempt to maximise public approval.

- Landscape appraisal needs to be signed off. Action RJ, KS and HD to review and send to Ian.

- Site Assessment – 1st draft review complete.

- Design codes is with Graziano for review.

- Local Green Space Assessment at final draft u[date stage.

- Draft plan is with Ian for review, Ian needs until the 26/02/21 to review.

Update from Ian:

- Plan – lot of repetition so producing a new document.

- Cut parts will be added to the end of the document for review by the group .

- 6 weeks will be needed for the pre-submission consultation with all residents of the village and business contained within.

- SPC must consult with community for 6 weeks = Regulation 14.

- Plan needs to be updated to reflect this time frame.

- Time frame allows to review comments and update plan.

- At the same time of the review Paul Bryant from BDC will screen the plan to identify if a EIA is required.

- Review by outside agencies also required e.g. Natural England they will approve in 99% of times.

- As no sites allocated by the NP it is unlikely that the threshold for EIA will be met.

- Local plan has allocated 1540 houses to Sproughton, BDC have to identify where the houses will go, no further requirement for NP to offer up further sites.

- Ian will handle the consultation phase for the group.

- Ian advises to speak to local landowners re the NP.

- A comments log will be needed for the review.

- Once review complete the plan can be submitted to BDC – Regulation 16.

- Prior to the independent review of the NP, BDC have between 5-8 weeks to complete their own consultation. This needs to be reflected in HD’s NP plan.

- Independent examiner is nothing to with BDC.

- Time frame from submission to BDC  completion is approx. 5 months.

- Ian needs photos for brochure.

Update from Rhona:

- Second grant application has been accepted – Alison and Ian to be paid.

- Possibility for further application for grant in April to finalise Ian’s payment.

- Public Consultation set for after 22/02/21

- Action Sharon – to establish cost for placing a leaflet in In Touch giving update on NP.

- Further from Helen – Nothing has been heard from Landbridge or De Zoete .

- Design codes to be published on website to influence Taylor Wimpy and Pigeon.

Next meeting is 08/03/21 at 18.30

Topics:

- Plan / Ian update

- Grant

- COVID19 and public consultation.

- All assessments to be signed off in next four weeks.